## Product Backlog
Product Backlog
User Story ID | User Story Name | Description | Size | Estimate | Priority | Status
0 | Create Initial App | As an end user, I want to be able to load a new game easily, so that I can avoid frustration or wasted time. | Large | 120 days | High | To Do
1 | Create User Auth | As an end user, I want to be able to sign in safely and securely, so that I can protect my privacy and personal identity. | Medium | 30 days | Medium | To Do
2 | Optimize Cloud Connection | As an end user, I want to play with minimal lag and game stutter of any kind, so that I can dominate like a boss! | Small | 20 days | Low | To Do

## User Story #0
User Story
ID | 0
Name | Create Initial App
Description | As an end user, I want to be able to load a new game easily, so that I can avoid frustration or wasted time.
Size | Large
Estimate | 120 days
Priority | High
Status | To Do
Acceptance Criteria | • App must be cloud-based and run (without major errors) on multiple platforms, including macOS, Windows, Linux, as well as iOS and Android (mobile)
• App must load games quickly and smoothly
• App must have an easy-to-navigate and aesthetically pleasing UI

## User Story #1
User Story
ID | 1
Name | Create User Auth
Description | As an end user, I want to be able to sign in safely and securely, so that I can protect my privacy and personal identity.
Size | Medium
Estimate | 30 days
Priority | Medium
Status | To Do
Acceptance Criteria | • User must be able to sign in to account using common sign-in methods on each operating platform
• App must use secure authorization and authentication using the industry-standard best practices
• User data must be stored on the cloud using advanced encryption algorithms

## User Story #2
User Story
ID | 2
Name | Optimize Cloud Connection
Description | As an end user, I want to play with minimal lag and game stutter of any kind, so that I can dominate like a boss!
Size | Small
Estimate | 20 days
Priority | Low
Status | To Do
Acceptance Criteria | • App must connect to cloud consistently and reliably on all operating platforms
• App must run smoothly without lag spikes or significant interruptions
• App must be scalable for a large number of users without slowing down or experiencing any other negative gameplay effects